{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":28,"n_cols":5,"rows_kept":28}
["进度数据"]
["步骤id","模块","任务","权重","备注"]
["int","string","string","int","string"]
["id","subModule","task","weight","remark"]
[1,"测量放线","竖向控制线测量放线",1]
[2,"测量放线","水平控制线测量放线",1]
[3,"预埋件安装","预埋件安装",1]
[4,"立柱安装","立柱准备",1]
[5,"立柱安装","立柱安装",1]
[6,"横梁安装","横梁安装",1]
[7,"层间防火安装","安装层间保温防火材料",1]
[8,"玻璃安装","安装玻璃",1]
[9,"嵌缝打胶","注密封胶",1]
[10,"装饰盖板安装","盖板",1]
[11,"清洗幕墙","橡胶刮板",1]
[12,"竣工验收","玻璃幕墙验收记录表",1]
[13,"测量放线","测量放线",1]
[14,"测量放线","标高定位",1]
[15,"预埋件安装","预埋件安装2",1]
[16,"连接件安装","竖龙骨立柱安装",1]
[17,"连接件安装","次龙骨横楞安装",1]
[18,"连接件安装","连接件固定",1]
[19,"镶挂石材板","石材安装",1]
[20,"嵌板缝密封胶","粘贴美容胶带",1]
[21,"嵌板缝密封胶","密封胶",1]
[22,"嵌板缝密封胶","撕掉美容胶带",1]
[23,"墙面清理","表面清理",1]
[24,"检查验收","检查验收",1]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0}